## Slide 1
Sub Heading
And Date
PROJECT MANAGEMENT IN PRACTICE
Lecture No: 6 Week: 3
Project Time Management
Vispi Shroff

## Slide 2: Recap
Importance of good project scope management
Methods of collection and documentation of requirements
Scope definition process
Contents of a project scope statement
Creating a work breakdown structure (WBS)
Different methods for creation
Importance of verifying scope
Controlling scope; avoiding scope creep

## Slide 3: Today’s Topics & Learning Outcomes
Importance of project schedules and good time management
Activity/Task Definition
Task Sequencing using diagrams and Dependencies
Next Time Management Lecture
Resource Estimation and Project Schedule
Optimisation Techniques
  Critical Path Analysis
  PERT (Program Evaluation and Review Technique)
Schedule Control

## Slide 4: Importance of Project Schedules
Time on projects tend to be the least flexible constraint.
Schedule is the main reason for conflicts
Delivering projects on time is cited as one of the biggest challenges by managers
Causes of Conflicts
Incorrect estimation to begin with
Lack of change control
Lack of planning
Myers-Briggs Type Indicator (J vs P)
Cultural Differences

## Slide 5: Project Time Management
Define Activities
Sequence Activities
Estimate Activity Resources
Controlling the Schedule
Estimate Activity Durations
Develop Schedule

## Slide 6: Define Activities
Derived from your WBS.
Decompose to the level of detail required
Activity Lists – Name, ID, Description
Activity Attributes – Predecessors, Successors, Logical Relationships, constraints, imposed dates, assumptions.
Milestones – Significant event, useful for goal-setting and monitoring progress.

## Slide 7: Sequencing Activities
Review Activities to determine dependencies and relationships.
Review an activity to determine what other activities it is dependent upon, if any, for it to begin.
Review an activity to determine what other activities it is dependent upon, if any, for it to finish.
You must determine dependencies to use Critical Path Analysis
Use network diagrams to map these dependencies.
  It is a “schematic display of logical relationships among, or sequencing of, project activities.
  Two forms – Arrow and Precedence Diagramming methods

## Slide 8: Types of Dependencies
Mandatory dependencies (hard logic): inherent in the nature of the work being performed on a project.
Discretionary dependencies (soft logic): defined by the project team; sometimes referred to as soft logic and should be used with care since they may limit later scheduling options
External dependencies: involve relationships between project and non-project activities

## Slide 9: Arrow Diagramming Method
Also known as Activity-on-Arrow (AOA) network diagrams
- Activities represented by arrows, nodes/circles are start and end points, and can only show Finish-to-Start dependencies.

## Slide 10: Precedence Diagramming Method
More popular, used by PM software.
-Activities represented by boxes, arrows showing relationships.

## Slide 11: Precedence Diagram

## Slide 12: Classroom Activity

## Slide 13: Any Thoughts, Questions, Ideas?
- September 11, 2003

## Slide 14: Reading Materials for the Week
Schwalbe, K. – Information Technology Project Management, Chapter 6
PMBOK – Chapter 6
We’ll be looking at
Estimating Resources & Duration
Critical Path Analysis
PERT

## Slide 15: Conclusions
We looked at
Importance of Time Management
Time Management Processes
Activity Definition
Sequence of Activities

## Slide 16: References
Schwalbe, K. – Information Technology Project Management, Chapter 6
PMBOK – Chapter 6
Dilbert.com – September 11, 2003