## Slide 1
Sub Heading
And Date
PROJECT MANAGEMENT IN PRACTICE
Lecture No: 17 Week: 10
Earned Value Management - Revisited
Vispi Shroff
vispi.shroff@ul.ie

## Slide 2: Earned Value Management
- Commonly used performance measurement technique
It integrates
  Scope
  Time
  Cost
Requires an integrated baseline against which performance can be measured.
Requires actual project data to obtain realistic measurements of project performance.
EVM Develops and monitors three key dimension for each activity from a project’s WBS
  Planned Value (PV), Earned Value (EV), Actual Cost (AC)

## Slide 3: Planned Value (PV)
- Planned value (PV) is the authorised budget assigned to the activity or WBS component.
Also called budget for that activity.
Budget for all activities when totalled is Budget at Completion (BAC).
It is the portion of the approved cost estimate planned to be spent on a activity during a given period of time.
Part of a digital media design project for development of a portfolio website includes the purchase and installation of a web server. Estimated cost for the activity is €5000, and time estimated is 1 week.
PV for that activity for that week is €5000.

## Slide 4: Actual Cost (AC)
Total costs incurred to accomplish the work on an activity during the given period.
AC must correspond to the definition of what was budgeted in the PV (eg. Direct hours only, direct costs only, direct and indirect costs, etc)
AC has no upper limit, and reflects whatever is spent to achieve the work.
The purchase and installation of the web server took 2 weeks. It cost €10000 in total. €7,500 of that was incurred during Week 1, and €2,500 was incurred during Week 2.
The AC for the WBS component/activity in Week 1 is €7,500.
The AC for the WBS component/activity in Week 2 is €2,500.

## Slide 5: Earned Value (EV)
Estimate of the value of the work performed/actually completed.
It is based on the original planned costs and the rate at which the team is completing the work.
The rate at which the team is completing the work is also known as Rate of Performance.
EV cannot be greater than the planned value of the activity/WBS component.
If only 50% of the work involved in purchasing and installing the web server was completed by the end of Week 1, the RP is 50%.
So, the EV at the end of Week 1 for that activity is RP*PV, i.e. 50% of the planned value, ie.. 50% of €5000 = €2,500

## Slide 6: Variances
Variances from the baseline should be calculated using the values determined above.
These variances assist in indicating the future performance of the project, and can be used to provide efficiency indicators.
Variances can be used to provide comparisons against prior projects or the portfolio.
The two variances are
  Schedule Variance (SV)
  Cost Variance (CV)
Negative numbers indicates problems in that area.

## Slide 7: Schedule Variance
- It is a measure of the schedule performance on a project
Useful to indicate that a project is falling behind it’s baseline schedule.
SV=EV-PV
At completion, SV will be zero, as all the planned values will be earned by the completion of the project.
The SV for the web server purchase and installation at the end of Week 1 is
SV= EV-PV
= 2,500-5,000
SV = - 2,500

## Slide 8: Cost Variance (CV)
Cost Variance is a measure of the cost performance on a project.
Critical because it indicates the relationship of performance to the money spent.
Generally, negative CVs and non-recoverable.
CV = EV – AC
The CV for the webserver purchase and installation for Week 1 is
    CV = EV-AC
    = 2,500 – 7,500
    CV = -5,000

## Slide 9: Performance Indices
Variances can be used to calculate performance indices which can be used to determine efficiencies
Useful in forecasting future performance of the project
Useful for comparisons against other similar projects or projects in the same portfolio.
Two performance indices used are
  Schedule Performance Index (SPI)
  Cost Performance Index (CPI)

## Slide 10: Schedule Performance Index (SPI)
It is a measure of progress achieved compared to the progress planned on the activity or project.
It is the ratio of the Earned Value to Planned Value.
An SPI less than 1.0 indicates a project is behind schedule.
An SPI equal to 1.0 indicates a project is on schedule.
An SPI greater than 1.0 indicates a project is ahead of schedule.
SPI = EV/PV
In the case of the web server activity,
  SPI = EV/PV
  = 2500/5000
  SPI = 0.5

## Slide 11: Cost Performance Index (CPI)
It is a measure of value of work completed compared to the actual cost or progress planned on the activity or project.
It is the ratio of the Earned Value to Actual Cost.
An SPI less than 1.0 indicates a cost overrun on the project.
An SPI equal to 1.0 indicates a project is on budget.
An SPI greater than 1.0 indicates a cost underrun on the project.
CPI = EV/AC
In the case of the web server activity,
  CPI = EV/AC
  = 2500/7500
  CPI = 0.33

## Slide 12: Estimate at Completion (EAC)
It is an estimate of what it will cost to complete a budget based on performance to date
EAC = BAC/CPI
If the BAC for the digitial media design project was €25,000, then
    EAC = BAC/CPI
    = 25,000/0.33
    EAC = 75,757

## Slide 13: An Example…
Following are the values for a one-year project when measured at month 2.
PV= €23,000
EV=€20,000
AC=€25,000
BAC=€120,000
-Calculate CV, SV, CPI, SPI
Is the project on schedule?
Is the project on budget
Calculate the EAC
Calculate how long will it take to complete the project.

## Slide 14: Any Thoughts, Questions, Ideas?

## Slide 15: References
Schwalbe, K.. 2007 – Information Technology Project Management, Chapter 7
PMBOK Guide, 4th Ed – Chapter 7
Dilbert Comics