## Slide 1
Sub Heading
And Date
SOFTWARE PARADIGMS
Scrum: Theory and Practice
Vispi Shroff

## Slide 2: What’s in a Name?
Not an acronym
Based on a practice within the methodology which the co-creators thought was representative of a Scrum.
Co-created by Jeff Sutherland and Ken Schwaber, but term and many ideas originally credit to (Takeushi & Nonaka, 1986)
Scrum Principles from the Agile Manifesto
- Individuals and interactions over processes and tools
- Completed functionality over comprehensive documentation
- Customer collaboration over contract negotiation
- Responding to change over following a plan

## Slide 3: Scrum at a Glance

## Slide 4: The roles people play
Product Owner: In charge of the project deliverables, product decisions, backlog ownership.
Scrum Master: Ensures the team functions cohesively and productively. The Scrum Master is the facilitator and the ‘obstacle remover’ for the Scrum Team.
Scrum Team: Self-organised and self-directed work team. It important to have an experienced developers in a Scrum Team.

## Slide 5: Important Scrum Activities
Sprint Planning: Decide what is to be done in this sprint, with the Product Owner
Daily Scrum Meeting: A daily stand-up meeting where the team’s progress is mapped, difficulties are shared, etc. Should be short.
Sprint Review: Go through the items completed in the Sprint with the Product Owner
Sprint Retrospective: Review how to improve the product and the processes being used

## Slide 6: Scrum Artefacts
Product Backlog: Prioritised list of all the functionality which the client desired to be implemented. Higher priority functionality is more finely defined.
Sprint Backlog: Set of work from the product backlog which the team agrees to complete for a given sprint.
Burndown Charts: Progress charts of work completed over the duration of a sprint, a easy visual indication of progress made over the sprint.

## Slide 7: A Scrum Implementation
The Official Line
Background of the company
Problems being faced at the time of Scrum implementation
  Growing troubles
  No change management
  Spaghetti Code
  Adding a new features of was introducing 3-5 issues with existing features.
  No idea of what we could/would deliver or when we would be able to deliver it.

## Slide 8: The 1st Sprint – Aug 2006
A bug fixing sprint, team of 3 developers and 1 QA person
Estimated time: 1 month
Delivery time: 2 months
Problems included broken builds, bugs marked as fixed not actually fixed, a very time consuming build process.
Lessons learnt and processes implemented included code reviews by fellow developers, developer testing and a requirement for an shortened and automated build process.

## Slide 9: Over subsequent sprints
Continued to deliver late, but the % of delay kept reducing.
Our sprints varied in duration from 2 months to 4 months.
At its height, team comprised of 6 developers and 2 QA people.
Product was slowly but steadily re-designed.
Different Scrum Masters & Product Owners
CTO left the company, other organisational problems
The stand-up meetings weren’t stand-up, and team tensions were beginning to spill over in the meetings
All employees were made redundant in June 2007 and operations were shut down.

## Slide 10: A new chance – October 2007
Company was reformed three months later, only 3 of the original 9 employees returned.
Lessons were learnt from previous sprints.
We hired people with many years of industry experience.
Moved away from daily stand-up meetings to individual schedules managed on a daily basis.
We did fixed length sprints of 2 months.
All the sprints were on time and had the functionality that the team had agreed on.

## Slide 11: Key Learning Lessons
You need experienced developers on your team
The more detailed the estimate, the better
You rarely get 8 hours of productivity on any given day
Just as with any business, other external factors can have significant impacts on the development efforts of the team.

## Slide 12: Any Thoughts, Questions, Ideas?

## Slide 13: References
Takeuchi, H. and I. Nonaka, 1986 - The New New Product Development Game. Harvard Business Review, 1986(January-February).
scrumalliance.org, 2010. Scrum Alliance - What Is Scrum? Available at: http://www.scrumalliance.org/pages/what_is_scrum [Accessed September 24, 2010].
Dilbert Comics, 2010.